## Checklist
Programme & Projects Governance Checklist
Trust Project Stage | Programme & Project Governance requirements | Template available on MicroGuide | [Name of project or programme] | [Name of project or programme] | [Name of project or programme] | [Name of project or programme] | [Name of project or programme] | Final doc confirmed Y/N | Key Notes
|  |  | [State type - project or programme?] | [State type - project or programme?] | [State type - project or programme?] | [State type - project or programme?] | [State type - project or programme?]
Initiation | Business Case (if required) | Yes | [6 empty] | http://intranet/website/staff/howdoi/businesscaseprocess/index.asp
Initiation | Project Brief (vision/strategy setting out aim or requirement for change). Including gathering any pre-change context / information | Yes |  |  | complete
Initiation | Programme Management Plan (PMP) or Project Initiation Document (PID) (include expected benefits, risks, mitigation, relevant priority) | Yes
Initiation | Programme leads confirmed |  |  |  | complete
Initiation | Executive Lead (SRO) |  |  |  | complete
Initiation | Clinical lead (if required) |  |  |  | complete
Initiation | Operational lead |  |  |  | complete
Initiation | Programme / Project Manager |  |  |  | complete
Initiation | Resource Plan (Quantify resource requirements and agree a resource plan [project manager/project support/improvement analysts/dev team/training] (depending on size and scope) | See Key Notes | [6 empty] | Please contact Transformation & Informatics mailbox for resource profile template
Initiation | Non-Financial benefits identified | See Key Notes |  |  | in progress |  |  |  | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Initiation | Financial benefits (added to Cost Improvement tracker) | See Key Notes |  |  | in progress |  |  |  | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Initiation | Stakeholders matrix (include suppliers if relevant)/Stakeholder Map | Yes |  |  | in progress
Planning | Engagement and communications plan [for digital include apps support, testing, training, IT ops, IT infrastructure]; include patient engagement | Yes |  |  | in progress
Planning | Specific engagement plan for patients and public (include focus groups, experienced based design co-design, surveys and feedback) - link to patient experience team (PPI request form) | Yes | [6 empty] | https://viewer.microguide.global/guide/1000000334#content,4363b8dd-b9ef-4ec0-bd99-c2f0255988db
Planning | Driver Diagram | See Key Notes | [6 empty] | Please contact Transformation & Informatics mailbox for driver diagram resources
Planning | Project / programme milestone plan (Gantt) | Yes |  |  | in progress
Planning | QIA (quality impact assessment) | Yes |  |  | n/a
Planning | DPIA (data protection impact assessment) & Rapid DPIA | Yes |  |  | in progress |  |  |  | Information Governance - General Data Protection Regulation (GDPR)
Planning | Equality Impact Assessment (EIA) | Yes | [6 empty] | Equality Impact Assessment Tool (microguide.global)
Planning | Clinical Safety Report (for digital change) | Yes | [6 empty] | Clinical risk management standards - NHS Digital
Planning | RAID log (Risk, Assumptions, Issues, Dependencies) | Yes |  |  | in progress
Planning | System specification (if required) | [7 empty] | Refer to Procurement for requirements specification template if required for tendering. Suppliers will be expected to provide system (technical) specificationif asset being purchased
Planning | Agree Core KPIs (link to corporate objectives) | [7 empty] | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Planning | Establish Data sources/Dashboard | [7 empty] | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Planning | Gather Baseline data/metrics (incl. GIRFT, Model Hospital, NHS Benchmarking, Dr Foster, Internal data sources) |  |  |  | complete |  |  |  | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Planning | Set up benefits tracker | Yes | [6 empty] | Please contact Transformation & Informatics mailbox for Benefits Identification & Tracker template(s)
Planning | Standard Operating Procedures in place | Yes |  |  | not started
Planning | Sustainability Assessment (baseline) | Yes |  |  | not started
Planning | EIA (equality impact assessment) |  |  |  | n/a
Delivery | Establish Monthly Programme Board & TOR | Yes |  |  | in progress
Delivery | Agree escalation process (e.g board)
Delivery | Set up whole system programme board (if relevant)
Delivery | Workstreams established/Task and finish groups |  |  |  | not started
Delivery | Monthly highlight report/board report established | Yes |  |  | complete
Delivery | Process to review risks monthly established (with escalation to risk register as needed)
Delivery | Lessons learned recored and monitored | Yes
Delivery | Release management (IT projects) | Yes | [6 empty] | Release note
Closing | Annual Lessons Learned report | Yes |  |  | not started
Closing | Post project evaluation/end of year programme summary/report | Yes |  |  | not started
Closing | Handover to BAU (business as usual)
Closing | Handover to BAU planned, with documentation [e.g. test script, sops etc.) | Yes |  |  | not started
Closing | Data retention/destruction assessment (IT projects) | [7 empty] | Information Governance - General Data Protection Regulation (GDPR)
Closing | Security testing pre-go live (IT projects) | [7 empty] | For IT projects, the Project Manager must ensure that Informatics will run a NESSUS scan to perform penetration testing. Results will be recorded in IT Release Note, for which there is a template
complete
In progress
not started