## Slide 1: Terms of Reference: DATE
The PMB meets every 4 weeks and is focused on reviewing savings / income initiatives, unblocking issues, escalating issues to OETMG and reviewing the Theatres Programme Plan and Charters to ensure delivery. Also provides a forum to share key learnings and support teams to overcome their challenges. Core members are expected to be represented if absent.
Purpose & Key Objectives
Chair: Surgery Clinical Director
Deputy chair:
Operational lead: Deputy chair:
MSK Clinical Director, Head of Transformation, Directorate Finance Manager, PMO Lead, MSK & Surgery Directorate Managers, Surgery Deputy Directorate Manager, Theatres Manager
Core Members
Review prior actions
Finance and operational performance
Key Milestones
Key priorities, consider
  Initiative plans & delivery status
    Key issues to unlock / escalate
    Key learnings to share
Interdependencies/ risks/ support
For Decision today
Standing agenda
Review initiatives
Review progress against plans
Tackle cross cutting issues
Identify strategies to unlock problems
Share learnings across directorates
Escalate key issues to OETMG
Meets every 4 weeks
PMO to share templates to be completed one week prior
Materials circulated 24 hrs prior
CD to chair /PMO provide action log
Actions communicated within 24 hrs
Operations
Charter & scheme status updates
Specific initiative charters
Finance updates (Finance)
Inputs
Actions
Outputs
PMB is a time for updates on progress and to share learning
OET Board
Trust Board
PMB
Directorate Mgmt.
Committee
OET Mgmt. Group
Finance esc. committee
PMO
Exec Sponsor
Clinical Director
DM